## Sheet1
HEI | Programme | Status | Description | Estimated Completion
University College Cork (UCC)
Enterprise Deep Retrofit | EEDPP 2021 | 2 Phase Delivery Proposal. Phase 1 complete September 2023. Phase 2 programmed for implementation summer 2024, no update since pause Q1 2024. | Deep Retrofit | Q3 2024
DUBLIN CITY UNIVERSITY (DCU)
Polaris Building (Future Technology Building) | Other Co-Funded | On site | The project will provide a new 4 storey state-of-the-art science, technology, engineering and mathematics (STEM) facility of 9,234m2. | Q3 2024
NUI DUBLIN (UCD)
Future Campus Phase 1 | HESIF I | On site | The works involve the delivery of the 11,581m2 Centre for Future Learning building. | Q3 2025
O' Brien Centre for Science | HESIF II | On site | The project will provide a 8,815m2 extension and 14,213m2 refurbishment of re-imagined educational and research space. | Q1 2026
NUI MAYNOOTH (MU)
Technology, Society and Innovation Building | HESIF I | Arts Project Element on site | The project consists of a new build of 10,554m2 teaching and learning facility and a 5,670m2 refurbishment of the existing Arts building and some parts of the Callan and Science Building at MU. The TSI New Building element achieved substantial completion 6 July 2022. The Callan reconfiguration element element achieved substantial completion on 23 September 2022. The car park and bus terminus elements of the project were handed over in Q1 2023.The new student common room (Arts Phase 1) was completed and achieved BCAR registration by 26 September 2023.The Arts Phase 2 refurbishment element is programmed for implementation during summer period 2024. | Q4 2024
TRINITY COLLEGE DUBLIN TCD
E3 Learning Foundry | Other | On site | This is a major project for the Engineering, Environment and Emerging Technologies (E3) learning foundry on TCD’s main campus with a 7,288m2 extension and a 2,686m2 refurbishment . | Q3 2024
MTU (Cork and Tralee)
Refurbishment of 1974 Building | IURF | Phase 6 on site | Extensive upgrade and refurbishment of the 1974 Building of 30,000m2 at the Cork Campus, Bishopstown. | Q4 2024 (phase 6) Overall project Q4 2026
Melbourn Building | EEDPP 2021 | On site | Deep Fabric Retrofit | Q2 2024
Atlantic Technological University (Galway-Mayo, Sligo and Letterkenny)
ATU Sligo - Block K&L | IURF | Block K (263m2 New Build & 1,043m2 Refurb) and L (1,655 m2 New Build & 1,562m2 Refurb)complete. Vacated space works (260m2 Refurb) on-going. | The repurposing of space left on the main campus as a result of all design programmes moving to K & L Blocks. | Q4 2024
ATU Sligo - Blocks G&P | EEDPP 2023 | On site | Heating Decarbonisation and Energy Retrofit of Blocks G and P | Q4 2024
ATU Galway - Creative Centre for Art and Media (CCAM) | EEDPP 2021 | On site | Medium Retrofit with High Temp air source Heat Pump | Q4 2024
South East TU (SETU) (Carlow and Waterford)
Carlow campus Burrin Building | EEDPP 2021 | On site | Medium Retrofit with High Temperature Heat Pump | Q4 2024
Dundalk Institute of Technology
North & South Building Refurbishment, STEM extension | IURF | North Building Roof with M&E works on site | Medium Retrofit with High Temperature Heat Pump | Q4 2024(for North Building Roof with M&E work package)
Univeristy of Limerick
IBC2 | EEDPP 2021 | 2 Phase Delivery Phase 1 - on site Phase 2 - pre-tender | Phase 1: Works commenced in January 2024, Phase 2 under review as a result. | Phase 1: - Q4 2024