1. Table of delayed DHLGH Commitment Items 
	CI No.
	Commitment

	Mission
	Submission
	Timeframe Specified in PfG
	Current Status
	Comment

	1454
	Task the new Electoral Commission to examine the issue of the use of posters at elections and referendums within 12 months of its establishment, and consult on placing limitations on the number of posters that can be used or fixing certain locations for their use. The Government will legislate for its recommendations in advance of the 2024 Local Elections.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	2024 Local Elections
	Delayed
	
In support of this commitment the Minister wrote to An Coimisiún Toghcháin and outlined a number of issues that An Coimisiún might include in its initial research programme. This correspondence included CI1454 relating to posters. Subsequently, An Coimisiún’s draft research programme, published on 10 November 2023, included a proposal to examine the use of posters at elections and referendums.

An Coimisiún’s finalised research programme was published on 10 July 2024 and includes a proposal to examine the use of posters at elections and referendums. Policy regarding the use of posters at elections and referendums will be reviewed in light of any recommendations made by An Coimisiún when it has considered the issue.


	372
	Launch a new revised and strengthened River Basin Management Plan in 2022, drawing on a collaborative approach between all stakeholders.
	A Green New Deal
	Water
	2022
	Delayed
	
The third River Basin Management Plan was approved by Minister O'Brien and noted at Cabinet in July. Launch/publication of the RBMP is scheduled for 5th September.

	370
	Ensure that the State complies with the EU Water Framework Directive.
	A Green New Deal
	Water
	2022
	Delayed
	
The third River Basin Management Plan was approved by Minister O'Brien and noted at Cabinet in July. Launch/publication of the RBMP is scheduled for 5th September. Outstanding infringement cases will need to be resolved to confirm compliance.
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2. Table of Completed DHLGH Commitment Items 
	CI No. 
	Commitment

	Mission
	Sub Mission
	Current Status

	82
	Set out how commercial rates will be treated for the remainder of 2020.
 
	Reigniting and Renewing the Economy
	A Jobs led Recovery
	Completed - January 2021

	249
	Every minister will make climate action a core pillar of their new departmental strategies, which must be produced within six months of the Government taking office. 
	A Green New Deal
	Emissions
	Completed - The Department's Statement of Strategy was published on 19/4/2021 and included climate action as a core pillar. 

	282
	Conclude the review of the current planning exemptions relating to solar panels, to ensure that households, schools, and communities can be strong champions of climate action. 
	A Green New Deal
	Energy
	Completed - Revised Solar exemption regulation were signed into effect on 5 October 2022.

	356
	Retain Irish Water in public ownership as a national, standalone, regulated utility.
	A Green New Deal
	Water
	Completed - From 1 Jan 2023, Uisce Éireann is the national authority for water services with responsibility for the functions assigned to it by or under the Water Services Acts 2007 to 2022.

	579
	Move away from dormitory-style accommodation on a long-term basis and aim to provide suitable tenancies. 
	Housing for All
	Homelessness
	Completed - the Department published Guidelines for New Emergency Accommodation in September 2022.

	581
	Develop a National Youth Homelessness Strategy.
	Housing for All
	Homelessness
	Completed - The Youth Homelessness Strategy was launched on 9 November 2022.

	582
	Continue the Housing Agency’s Acquisition Fund to purchase vacant stock from financial institutions. 
	Housing for All
	Homelessness
	Completed - On 26 March 2024, the Department of Public Expenditure, NDP Delivery and Reform formally sanctioned the re-purposing of the Housing Agency Acquisitions Fund for a dual role to support both the Cost Rental Tenant in-Situ (CRTiS) Scheme and the Housing First Programme.

	586
	Bring forward a target for the delivery of affordable homes over the lifetime of the Government, to be available for qualifying purchasers as a matter of priority. Recognising the ambition of the Government in this area, these homes could be delivered through a number of channels including local authorities (Serviced Sites Fund), introducing affordable homes requirements to Part V and the Land Development Agency and will be sold through the State-backed Affordable Purchase Scheme. 
	Housing for All
	Affordable Home Ownership
	Completed - Affordable housing delivery targets for the period 2022 to 2026 were issued to local authorities in March 2022. 

	589
	Retain and expand the Help to Buy scheme for new properties and self-build properties.
	Housing for All
	Affordable Home Ownership
	Completed - The Finance Bill (No. 2) 2023, was published by the Minister for Finance on 19 October 2023.

	590
	Expand the Rebuilding Ireland Home Loan. 
	Housing for All
	Affordable Home Ownership
	Completed - An expanded and reformed Local Authority Home Loan was introduced on 4 January 2022.

	595
	Put in place the appropriate controls to allow local authority discretionary funding to increase from €2m to €6m for social housing projects.
	Housing for All
	Public and Social Housing
	Completed - Circular 28/2020 was issued on 14/09/2020.

	611
	Reform the Fair Deal scheme to incentivise renting out vacant properties. 
	Housing for All
	Rental
	Completed - The Nursing Home Support Scheme Act 2009 (Assessment of Eligible Rental Income from Principal Private Residences) Order 2023 was signed on 04 December 2023.

	614
	Examine the measures that may be needed to support tenants, as a result of COVID-19, informed by the forthcoming research from the Economic and Social Research Institute (ESRI).
	Housing for All
	Rental
	Completed - Tenacy protections came into effect from 1 August 2020

	615
	Extend the moratorium on the termination of tenancies, in line with public health advice, if the requirements of Section 4 of the Emergency Measures in the Public Interest (Covid-19) Act 2020 are met.
	Housing for All
	Rental
	Completed - The Residential Tenancies Act 2020  was enacted and came into operation on 24 October 2020. The Act modifies the operation of the Residential Tenancies Acts 2004-2020

	616
	Legislate to establish the Land Development Agency (LDA) on a statutory basis, as a matter of urgency (see detail on p56 of PfG).
	Housing for All
	Land Development Agency
	Completed - All remaining provisions of the Land Development Agency Act were commenced on 1 January 2023.

	618
	Ensure that development of sustainable communities is the core objective of the LDA, delivering sustainable, climate resilient, low-carbon housing. 
	Housing for All
	Land Development Agency
	Completed - The Land Development Agency Act 2021 was signed into law in July 2021.

	619
	Task the LDA with driving strategic land assembly, to ensure that the sustainable development of new and regenerated communities is well served by essential services. 
	Housing for All
	Land Development Agency
	Completed - The Land Development Agency Act 2021 was signed into law in July 2021.

	622
	Allocate Compulsory Purchase Order powers to the LDA. 
	Housing for All
	Land Development Agency
	Completed - The Land Development Agency Act 2021 was signed into law in July 2021.

	623
	Complete the audit of state lands, identifying land banks in public ownership that are suitable for housing and other purposes. 
	Housing for All
	Land Development Agency
	Completed - The LDA have submitted a Report on Relevant Public Land in advance of the statutory deadline of 30 March 2023. 

	624
	Mandate the LDA to work with local authorities, state agencies and other stakeholders to develop masterplans for strategic sites. 
	Housing for All
	Land Development Agency
	Completed - The Land Development Agency Act 2021 was signed into law in July 2021.

	628
	Ensure that any state lands being offered for sale, whether owned by a local authority, government department, commercial or non-commercial semistate agency or any other agency, would automatically be offered first to the LDA. 
	Housing for All
	Land Development Agency
	Completed - The Land Development Agency Act 2021 was signed into law in July 2021.

	630
	Examine the issue of defective housing in the first 12 months, having regard to the recommendations of the Joint Oireachtas Committee on Housing report, ‘Safe as Houses’.
	Housing for All
	Land Development Agency
	Completed - The Minister received Government approval to draft legislation to establish supports for the remediation of fire safety, structural safety and water ingress defects in purpose-built apartment buildings, including duplexes, constructed between 1991 and 2013, on 18 January 2023. 

	649
	Not extend Strategic Housing Developments beyond their legislative expiry in 18 months’ time. 
	Housing for All
	Planning and Reform
	Completed - The Planning and Development (Amendment) (Large-scale Residential Development) Act 2021 (Act of 2021) was signed into law on 14 December 2021.

	651
	Establish a Commission on Housing to examine issues such as tenure, standards, sustainability, and quality-of-life issues in the provision of housing.
	Housing for All
	Planning and Reform
	Completed - the Housing Commission was formally established in December 2021.

	1425
	Examine ways to further streamline the commercial rates system post COVID-19.
	Reforming and Reimagining our Public Life

	Local Government
	Completed - A new legal framework for commercial rates will be in place for 2024 onwards.

	1427
	Pass legislation to allow the first directly elected mayor in Limerick to be elected in 2021. Support the first directly elected mayor with a financial package to deliver upon their mandate. 
	Reforming and Reimagining our Public Life

	Local Government
	Completed - Local Government (Mayor of Limerick) and Miscellaneous Provisions Bill 2023 was signed on 6 March 2024.

	1428
	Allow for plebiscites to be held in 2024 in any local authority that wishes to have a directly elected mayor. Demand will be demonstrated at the request of the local authority or by way of a petition from 20% of registered voters.
 
	Reforming and Reimagining our Public Life
	Local Government
	Completed - Plebiscite provisions in the Local Government (Mayor of Limerick) and Miscellaneous Provisions Bill 2023 which was signed on 6 March.

	1429
	Where directly elected mayors are being established, we will transfer powers from the city and county managers to mayors directly elected by the people for a five-year term.
	Reforming and Reimagining our Public Life
	Local Government
	Completed - This is the policy approach approved by Government in the context of the directly elected mayor for Limerick.

	1433
	Implement the Moorhead Report on the Role and Remuneration of Local Authority Elected Members within 12 months.
	Reforming and Reimagining our Public Life

	Local Government
	Completed - Implemented with effect from July 2021.

	1451
	Establish an Electoral Commission to provide independent oversight of elections and referendums, to inform the public about elections and referendums, to update and maintain the electoral register, and to conduct elections. Ensure that this Commission is in place by the end of 2021. 
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	Completed - An Coimisiún Toghcháin was established on 9 February 2023.

	1489
	Create a strategic policy unit for the complex data analysis, programme evaluation and policy development within each department charged with delivery in such core areas.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	Completed - December 2020.








3. [bookmark: _Toc163135143]Table of Ongoing DHLGH Commitment Items
	CI No. 
	Commitment
	Mission
	Sub Mission
	Timeframe Specified in PfG
	Status

	5
	Using the National Planning Framework as a template, develop a Town Centre First policy, modelled on the scheme developed by the Scottish Government and informed by the Town Centre First pilot project.
	A Better Quality of Life for All
	Town Centres First
	None
	On Schedule for completion in the stated timeline

	6
	Prioritise a Town Centres First collaborative and strategic approach to the regeneration of our villages and towns, using the Collaborative Town Centre Health Check (CTCHC) framework to gather data and lead actions.
	A Better Quality of Life for All
	Town Centres First
	None
	On Schedule for completion in the stated timeline

	8
	Provide seed capital to local authorities to provide serviced sites at cost in towns and villages, to allow individuals and families to build homes.
	A Better Quality of Life for All
	Town Centres First
	None
	On Schedule for completion in the stated timeline

	75
	Establish sectoral taskforces, comprising Government, independent experts and stakeholders and chaired by line ministers, to focus on the specific needs of sectors and to bring forward plans in the context of the National Economic Plan.
	Reigniting and Renewing the Economy
	A Jobs led Recovery
	Immediately
	On Schedule for completion in the stated timeline

	101
	Mobilise agencies, public and private, to focus on strengthening the capacity of enterprises in critical areas and encourage the uptake of structural changes that will make enterprises more resilient for the longer term.
 
	Reigniting and Renewing the Economy
	National Economic Plan
	None
	On Schedule for completion in the stated timeline

	162
	Strengthen the Mortgage to Rent Scheme and ensure that it is helping those who need it.
	Reigniting and Renewing the Economy
	Public Finances and Taxation
	None
	On Schedule for completion in the stated timeline

	172
	The NPF is mandated for updating in 2024 and must respond to the evolving challenges across its strategic goals and be consistent with national policies.
	Reigniting and Renewing the Economy
	National Development Plan
	Before end 2024
	On Schedule for completion in the stated timeline

	196
	Work with the Northern Ireland Executive to deliver the flagship cross-border Ulster Canal project, in order to restore the all-island inland water system as a premier tourism attraction.
 
	Reigniting and Renewing the Economy
	Tourism
	None
	On Schedule for completion in the stated timeline

	245
	Evaluate and implement plans to realise the carbon sink potential of our marine environment, based on the introduction of Marine Protection Areas. 
	A Green New Deal
	Emissions
	None
	On Schedule for completion in the stated timeline

	250
	Each minister will  direct each of the agencies and offices under their department to adopt a climate mandate, under which those bodies will seek to support climate action within their own operations and among their clients and suppliers.
	A Green New Deal
	Emissions
	None
	On Schedule for completion in the stated timeline

	269
	Finalise and publish the Wind Energy Guidelines, having regard to the public consultation that has just taken place. 
	A Green New Deal
	Energy
	None
	On Schedule for completion in the stated timeline

	342
	Review the remit, status and funding of the National Parks and Wildlife Service (NPWS), to ensure that it is playing an effective role in delivering its overall mandate and enforcement role in the protection of wildlife.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	343
	Ensure that all local authorities have a sufficient number of biodiversity and heritage officers among their staff complement. 
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	344
	Support biodiversity data collection.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	346
	Review the protection (including enforcement of relevant legislation) of our natural heritage, including hedgerows, native woodland, and wetlands. 
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	347
	Develop a new National Invasive Species Management Plan.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	348
	Coordinate the actions in the Programme for Government regarding peatlands to maximise the benefits for biodiversity.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	349
	Introduce policies on supports for urban biodiversity and tree planting. 
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	351
	Continue to implement the third National Biodiversity Action Plan 2017-2021 and build on the commitments made at the first National Biodiversity Conference.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	352
	Support local nature groups and local authorities to work in partnership on local biodiversity projects. 
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	353
	Continue to raise awareness of biodiversity through initiatives like the Annual Biodiversity Awards Scheme.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	354
	Build on the success of the UNESCO Dublin Bay Biosphere and achieve further UNESCO designations for Irish sites, including the Lough Allen region.
	A Green New Deal
	Natural Heritage and Biodiversity
	None
	On Schedule for completion in the stated timeline

	357
	Ensure that Irish Water is sufficiently funded to make the necessary investment in drinking water and wastewater infrastructure. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	358
	Mandate Irish Water to develop plans to ensure security of supply and sufficient capacity in drinking and wastewater networks to allow for balanced regional development.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	359
	Fund Irish Water’s capital investment plan for drinking water and wastewater infrastructure on a multi-annual basis and deliver the €8.5 billion funding package committed to in Project Ireland 2040. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	360
	Support take-up of Irish Water’s Small Towns and Villages Growth Programme 2020-2024, which will provide water and wastewater growth capacity in smaller settlements that would otherwise not be provided for in Irish Water’s capital investment plan. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	362
	Support continued investment in reducing leakage across the network.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	363
	Fully consider the review from the Commission for Regulation of Utilities to Irish Water’s proposed approach to the Water Supply Project for the Eastern and Midlands Region.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	364
	Develop a scheme between local authorities and Irish Water to provide drinking water fountains nationwide to reduce plastic bottle litter.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	365
	Continue to help fund upgrades to wells.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	366
	Continue to help fund upgrades to domestic wastewater treatment systems, including septic tanks.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	367
	Review and work to improve the inspection regime for the 500,000 domestic wastewater systems and incentivise upgrading works. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	368
	Ensure that Irish Water progresses works to reduce the number of schemes on the Environmental Protection Agency’s (EPA) Remedial Action List.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	369
	Support Irish Water in its programme to remove lead pipes from the public supply.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	371
	Expand programmes, including the Agriculture Sustainability Support and Advisory Programme (ASSAP), and work with farmers, industry, and advisory services, to protect and deliver improvements in water quality. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	373
	Ensure that Irish Water develops Drinking Water Safety Plans to protect abstraction sources; and reduces public health risks, including Trihalomethane (THMs) exceedances in treatment plants.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	374
	Continue to support the Local Authority Waters Programme and expand the Community Water Development Fund. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	375
	Continue to provide a generous free allowance of water to every citizen to meet their basic everyday needs and provide an extra free allocation for people with specific health needs. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	376
	Implement the recommendations of the Committee on Future Funding of Domestic Water Services in relation to excess use.
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	378
	Conduct a feasibility study examining how further assistance can be given to low-income households for the installation of water efficient appliances. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	379
	Support the National Federation of Group Water Schemes, to ensure that issues of quality and security of supply are addressed.  
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	380
	Continue to invest in a multi-annual capital funding programme to improve the quality of drinking water in group water schemes, while protecting water quality. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	381
	Continue to work with An Fóram Uisce to review and develop water-quality strategies. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	382
	Commission a range of research projects to explore innovative ways of improving our water infrastructure and reducing consumption. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	383
	Review the electricity requirements of water and wastewater treatment plants and carry out a series of pilot projects to incorporate onsite renewable energy generation. 
	A Green New Deal
	Water
	None
	On Schedule for completion in the stated timeline

	546
	Embed ageing in place options for older people into the planning system, as the county and city development plans are redrawn this year.   
	Universal Health Care
	An Age-friendly Ireland
	Within the first year
	On Schedule for completion in the stated timeline

	547
	Drawing on the Housing Need and Demand Assessments, develop demographic reporting tools and population projections to gain a better national understanding of the needs and location of housing options for older people.   
	Universal Health Care
	An Age-friendly Ireland
	None
	On Schedule for completion in the stated timeline

	548
	Increase the provision of smaller homes in developments, ensuring that older people can remain living in their communities, close to essential services and facilities.
	Universal Health Care
	An Age-friendly Ireland
	None
	On Schedule for completion in the stated timeline

	549
	Task local authorities to work with Approved Housing Bodies, co-operatives, private developers, and Age Friendly Ireland on the development/redevelopment of older-person housing. 
	Universal Health Care
	An Age-friendly Ireland
	None
	On Schedule for completion in the stated timeline

	550
	Maintain support for the Housing Adaptation Grant Scheme.  
	Universal Health Care
	An Age-friendly Ireland
	None
	On Schedule for completion in the stated timeline

	575
	Increase funding and work with stakeholders, case workers and homeless people on a suite of measures to help rough sleepers into sustainable accommodation. 
	Housing for All
	Homelessness
	None
	On Schedule for completion in the stated timeline

	576
	Continue to expand the Housing First approach, with a focus on the construction and acquisition of one bed homes and the provision of relevant supporting services.
	Housing for All
	Homelessness
	None
	On Schedule for completion in the stated timeline

	578
	Ensure that Rent Supplement and Housing Assistance Payment (HAP) levels are adequate to support vulnerable households, while we increase the supply of social housing.
	Housing for All
	Homelessness
	None
	On Schedule for completion in the stated timeline

	583
	Increase funding for drug-free hostels.
	Housing for All
	Homelessness
	None
	On Schedule for completion in the stated timeline

	585
	Progress a state-backed affordable home purchase scheme to promote home ownership. 
	Housing for All
	Affordable Home Ownership
	None
	On Schedule for completion in the stated timeline

	587
	Extend the Serviced Sites Fund. 
	Housing for All
	Affordable Home Ownership
	None
	On Schedule for completion in the stated timeline

	588
	Provide seed capital to local authorities to provide serviced sites at cost in towns and villages to allow individuals and families build homes.  
	Housing for All
	Affordable Home Ownership
	None
	On Schedule for completion in the stated timeline

	591
	Explore expanding Part V to encompass affordable purchase and cost rental units. 
	Housing for All
	Affordable Home Ownership
	None
	On Schedule for completion in the stated timeline

	593
	Increase the social housing stock by over 50,000 over the next five-years, the majority of which is to be built by local authorities, Approved Housing Bodies and State agencies.
	Housing for All
	Public and Social Housing
	Over the next 5 years
	On Schedule for completion in the stated timeline

	594
	Ensure that an appropriate mix of housing design types is provided, including universally designed units, and accommodation for older people and people with disabilities. 
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	596
	Expand the role of Vacant Homes Officers in local authorities and support local authorities to bring vacant stock into productive use. 
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	597
	Work on a package of reforms with Approved Housing Bodies, to ensure that they can access finance and move off the balance sheet. 
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	598
	Introduce a social housing passport to allow households move from one local authority list to another.
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	599
	Maintain the right of social housing tenants to purchase their own home but require them to be in situ for 10 years, reduce the discount to a maximum of 25%, and give local authorities the first call on purchase.
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	600
	Standardise the differential rents regime across the country, to ensure fairness.
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	601
	Create a website to allow for choice-based letting on a nationwide basis.  
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	603
	Make local authority direct build housing projects, specific timelines and all gateway approval processes transparent and open to public oversight.
	Housing for All
	Public and Social Housing
	None
	On Schedule for completion in the stated timeline

	604
	 Develop a cost rental model for the delivery of housing that creates affordability for tenants and a sustainable model for the construction and management of homes. In doing this, we will be informed by international experience of the delivery of cost rental, such as the ‘Vienna Model’.
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	605
	Examine the creation of a system of holding rental deposits, informed by international experience.  
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	606
	Reduce our reliance on the use of HAP for new social housing solutions, as the supply of social and public housing increases.
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	607
	Mandate and resource the Residential Tenancies Board (RTB) to hear dispute resolution cases where deposits are concerned, so that the tenant can have their deposit returned to allow them secure another property, and to allow for swift resolution of disputes between landlords and tenants.
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	608
	Continue the RTB change programme, transforming it into an independent and strong regulator for tenants and landlords.
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	609
	Strengthen the regulatory and enforcement mechanisms, with regard to short-term lettings. 
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	610
	Support the adequate supply of rental accommodation by ensuring equity and fairness for landlords and tenants. 
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	612
	Improve the security of tenure for tenants, through legislating for tenancies of indefinite duration, increasing RTB inspections and enforcement, and examining incentives for long-term leasing.  
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	613
	Instruct local authorities, as part of their housing strategies, to undertake and publish a rental needs assessment. 
	Housing for All
	Rental
	None
	On Schedule for completion in the stated timeline

	617
	Ensure that all procurement carried out by the LDA has strong value-for-money protections and oversight.
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	620
	Provide homes for affordable purchase, cost rental and social housing through the LDA. 
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	621
	Ensure that the LDA Board includes a cross-spectrum of housing, financial, governance and other independent experts needed to fulfil its remit. 
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	626
	Require the LDA to give regular updates to the Oireachtas and review the legislation underpinning the LDA after a three-year period. 
	Housing for All
	Land Development Agency
	After a 3 year period
	On Schedule for completion in the stated timeline

	627
	Ensure that the LDA uses modern methods of construction, including offsite construction, to deliver high-quality, sustainable homes quickly and at scale. Local supply chains and labour should be used to increase community gain. 
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	629
	Ensure that the public housing rental stock on public lands is under the control of local authorities, Approved Housing Bodies, or other similar bodies.
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	632
	Ensure that the remediation fund for Pyrite and Mica is fully drawn down.
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	633
	Assist owners of latent defect properties, by identifying options for those impacted by defects, to access lowcost, long-term finance.
	Housing for All
	Land Development Agency
	None
	On Schedule for completion in the stated timeline

	635
	Introduce a ‘use it or lose it’ condition for all planning applications of 10 units or more. 
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	636
	Review and reform the judicial review process, so that such reforms come into effect upon the establishment of the Environmental and Planning Law Court, while always adhering to our EU law obligations under the Aarhus Convention.
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	637
	Examine the creation of an independent Building Standards Regulator to oversee building control nationwide and to act as custodian of the Building Control Management System, including the re-establishment of the Building Regulatory Advisory Body.
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	639
	Review how community gain can be captured through a review of the development levy process, rezoning systems, and planning permission conditions.
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	640
	Ensure that the Planning Regulator is adequately resourced and proactively engages with all stakeholders in the planning system, including informing and assisting the general public in contributing to local and regional development plans.
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	642
	Work to ensure that our ageing population has a range of options for living independently and that alternatives to long-term residential care to support ageing are in line with the policy statement ‘Housing Options for Our Ageing Population’.
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	643
	Avoid over-concentration of particular housing types in areas, by requiring local authorities to complete Housing Need and Demand Assessments to inform the delivery of an appropriate mix of housing typologies to cater for the needs of disparate household types and sizes. 
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	644
	Reform and consolidate Compulsory Purchase Order (CPO) laws.
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	646
	Strengthen enforcement of the Vacant Site Levy and the keep the legislation under review. 
	Housing for All
	Planning and Reform
	None
	On Schedule for completion in the stated timeline

	655
	Drive an informed and proactive engagement approach in the planning system. We will involve communities at an early stage and instil the concept of community gain. The new Office of the Planning Regulator will have a role in this regard.
	Balanced Regional Development
	 
	None
	On Schedule for completion in the stated timeline

	660
	Prioritise the upkeep and expansion of parks, green spaces, and other recreational infrastructure, for community enjoyment and biodiversity enhancement.
	Balanced Regional Development
	Rural Development
	None
	On Schedule for completion in the stated timeline

	673
	Acknowledge the ongoing importance and role of regional assemblies in management of EU funding programmes.
	Balanced Regional Development
	Rural Development
	None
	On Schedule for completion in the stated timeline

	757
	Publish a new National Pollinator plan and encourage public bodies to promote and protect biodiversity.  
	Balanced Regional Development
	Agriculture and Food
	None
	On Schedule for completion in the stated timeline

	775
	Review the effects of the nitrates derogation on water quality, in conjunction with the EPA, which will inform future policy in this area.
	Balanced Regional Development
	Agriculture and Food
	None
	On Schedule for completion in the stated timeline

	849
	Develop comprehensive legislation for the identification, designation, and management of Marine Protected Areas (MPAs) in Irish territorial waters. 
	Balanced Regional Development
	The Marine
	None
	On Schedule for completion in the stated timeline

	850
	Realise the outstanding target of 10% under the Marine Strategy Framework Directive as soon as is practical and aim for 30% of marine protected areas by 2030. This will be done on the basis of scientific expertise and in close consultation with all stakeholders, in particular the fishing industry, as well as environmental and community representatives. This consultation process will begin in the first 100 days of Government. 
	Balanced Regional Development
	The Marine
	Within the first 100 days
	On Schedule for completion in the stated timeline

	851
	Examine the establishment of an offshore maritime area as Ireland’s seventh national park. This would form part of the expanded MPAs and allow for a learning experience in the maritime environment. 
	Balanced Regional Development
	The Marine
	None
	On Schedule for completion in the stated timeline

	912
	Ensure that the housing needs of the Traveller Community are met by local authorities and ensure that existing funding is fully drawn down and utilised.
	A New Social Contract
	Equality
	None
	On Schedule for completion in the stated timeline

	945
	Work towards physical accessibility to all government departments, local authorities and agencies providing services.
	A New Social Contract
	Disability
	None
	On Schedule for completion in the stated timeline

	946
	Include the consideration of disability in all housing policy reviews.
	A New Social Contract
	Disability
	None
	On Schedule for completion in the stated timeline

	1102
	Examine ‘meanwhile use’ legislation for vacant buildings, with a view to its potential application in Ireland.
	Building Stronger and Safer Communities
	Arts and Culture
	None
	On Schedule for completion in the stated timeline

	1118
	Publish and implement the new all-of-government heritage policy and begin its nationwide implementation.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1119
	Explore multi-annual funding models and ensure that adequate funding is made available for the implementation of each County Heritage Plan.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1120
	Continue to support the role of the Heritage Officers in the areas of heritage education, health and wellbeing, and citizen science.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1121
	Encourage each local authority to appoint a Conservation and Repurposing Officer. 
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1122
	Build on community-led schemes, such as the Built Heritage Investment Scheme and the Structures at Risk Fund, which provide grant aid to protect and maintain important historic buildings in our local communities.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1123
	Encourage traditional building skills in devising an apprenticeship programme with the sustainable construction sector, focusing on heritage disciplines and crafts.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1124
	Expand the Heritage in School Scheme, so that more students can enjoy our rich natural cultural heritage.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1125
	Continue with the expansion of the National Inventory of Architectural Heritage and include modern and industrial buildings.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1126
	Continue to develop and implement a master plan of our National Parks and National Reserves.
	Building Stronger and Safer Communities
	 
	None
	On Schedule for completion in the stated timeline

	1296
	Seek to adopt an all-island approach to national planning frameworks.
	A Shared Island
	A Shared Island
	None
	On Schedule for completion in the stated timeline

	1301
	Promote an all-island approach to land-use planning and river-basin management plans to stop cross-border pollution. 
	A Shared Island
	A Shared Island
	None
	On Schedule for completion in the stated timeline

	1311
	Ensure that each government department maintains strong links with its Northern Ireland counterpart.
	A Shared Island
	A Shared Island
	None
	On Schedule for completion in the stated timeline

	1334
	Ensure that environmental marine conservation and pollution control measures are protected in bilateral relations.
	A Shared Island
	British-Irish Relations
	None
	On Schedule for completion in the stated timeline

	1391
	Hold a referendum on extending the franchise at presidential elections to Irish citizens living outside the State.
	At the Heart of Europe and Global Citizenship
	Strengthening our Relationship with the Diaspora
	None
	On Schedule for completion in the stated timeline

	1424
	Consider the expected Institute of Public Administration review of municipal districts, with a view to strengthening local democracy and identifying local needs and initiatives needed to strengthen and grow our communities, villages and towns in a sustainable manner. This review will examine the addition of directly elected, democratic bodies in such areas and below the municipal district level. 
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1431
	Examine the prospect of devolving more powers to the local authorities through the legislative process to strengthen and enhance local democracy.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1432
	Provide tailored and appropriate training to local authority members. 
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1434
	Enable councillors to access research and training to support them in their duties. 
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1435
	Require each council to publish an annual statement of accounts to all homeowners and ratepayers, giving a breakdown of how revenue was collected and how it was spent. 
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1436
	Enable local authorities to lead and collaborate on a ‘Town Centres First’ type approach to regenerate our towns and villages. 
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1437
	Review participatory structures to enhance statutory Part VIII processes.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1440
	Mandate the establishment of climate action SPCs in each local authority.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1441
	Consider the introduction of an alternate/substitute candidate list to cover parental and caring leave, longterm illness leave, resignation, career breaks and death in office.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1442
	Review and modernise of key performance indicators for local government, learning from metrics used in other jurisdictions.
 
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1444
	Develop a scheme between local authorities and Irish Water to provide drinking water fountains nationwide.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1445
	Ensure local authorities have regard to the National Planning Framework and alignment to the 17 UN Sustainable Development Goals (SDGs) when drafting development plans.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1447
	Empower local authorities to encourage improved gender and ethnic mix in local elections.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1448
	Require local authorities to be more flexible with meeting times and to use remote working technologies and flexible work practices to support councillors with parental or caring responsibilities, including childcare, and reduced travel times and absences from work.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1449
	Examine further mechanisms informed by best practice internationally to encourage political parties to select more women for the 2024 local elections.
	Reforming and Reimagining our Public Life
	Local Government
	None
	On Schedule for completion in the stated timeline

	1450
	Consider the recommendations of the National Women’s Council of Ireland (NWCI) report on Women beyond the Dáil, More Women in Local Government, with a view to reporting in 2021. 
	Reforming and Reimagining our Public Life
	Local Government
	Before end 2021
	On Schedule for completion in the stated timeline

	1452
	Empower the Electoral Commission to regulate online political advertising in the public interest and introduce a consistent regime relating to political advertising across all media.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1453
	Mandate the new Electoral Commission to examine the use of postal voting, with a view to expanding its provision.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1455
	Complete the modernisation process for voter registration, involving: (1) The simplification of forms and the registration process, including an online option; (2) A rolling (continuously updated) Electoral Register; (3) A single, national Electoral Register Database; and (4) A move to a system of identity verification, using one’s PPSN.
 
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1457
	Review our current electoral laws and the conduct of politics in Ireland, to ensure that donations and resources from non-citizens outside the State are not being utilised to influence our elections and political process. Legislate to prevent this, if necessary.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1458
	Examine replacing by-elections with an alternate list system.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1459
	Establish a fund to support political and electoral research by academics and researchers.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1471
	Hold referendum on housing. 
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1477
	Examine the Scottish experience of reducing the voting age to 17, in order to draw conclusions.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline

	1478
	Examine the time limitation on people who are temporarily living outside the State to remain on the voting register.
	Reforming and Reimagining our Public Life
	Political and Public Service Reform
	None
	On Schedule for completion in the stated timeline





