| Action Number | Actions | Output | Timeline | Status | Progress |
| --- | --- | --- | --- | --- | --- |
| AG/24/10 | Develop a detailed implementation plan for the translation of the Teagasc 2023 MACC and incorporation where appropriate into the Climate Action Plan | New/updated measures from the Teagasc MACC included in the Climate Action Plan | Q3 2024 | Complete | Action Complete |
| AG/24/16 | Develop a system for the monitoring and reporting of methane reducing feed and manure ingredients | Develop a system for the monitoring and reporting of methane reducing feed and manure ingredients | Q4 2024 | Delayed | Development of a monitoring & reporting system is progressing |
| AG/24/18 | Develop a pilot programme for the incorporation of methane reducing additives (enteric and manure) within the Signpost dairy farms | On-farm demonstration of the feasibility of the incorporation of methane reducing feed additives, and generation of farm specific carbon footprints | Q4 2024 | Complete | Action Complete |
| AG/24/26 | Development of ecosystem services through the creation of a carbon farming framework | Draft framework published | Q2 2024 | Delayed | Discussions on the development of policy for Carbon farming are progressing |
| AG/24/8 | Deliver a range of knowledge transfer activities promoting the importance and benefits to farmers of optimising nutrient management strategies as a key contributor to reduced gaseous emissions | Farmer engagement in Signpost Advisory Programme Engage and support 20,000 farmers in the Signpost Advisory Programme, 4,500 farmers in Derogation Scheme support and 15,000 farmers in ACRES. Analyse and provide feedback on at least 50,000 soil samples. | Q4 2024 | Delayed | Teagasc continues to deliver a range of knowledge transfer activities, and this action is progressing |
| JM/24/3 | Support piloting, demonstration and innovation for a sustainable and circular bioeconomy | Grant agreements in place with approved projects to advance initiatives for a competitive bioeconomy | Q4 2024 | Delayed | The grant agreements for approved projects are progressing |
| JM/24/5 | Support research, knowledge transfer and monitoring activities on rewetting measures for farmed peat soils through the Midlands Carbon Catchment Study | Consortium appointed to deliver on the objectives of the Midlands Carbon Catchment Study (MCCS) | Q4 2024 | Delayed | This action is progressing |
| LU/24/4 | Review the proposed measures detailed in the Teagasc MACC to determine which actions are possible to deliver sustainably across all land use types | Report completed & under consideration | Q3 2024 | Complete | Action Complete |
| AG/23/23 | Consider the recommendations arising from the NESC report on Just Transition in Agriculture and develop suitable responding actions for inclusion in CAP 24. | Implementation Report with a focus on engagement, resources and policy. | Q3 2023 Delayed | Complete | Action Complete |