	Action Number 
	Actions 
	Output 
	Timeline 
	Status 
	Progress 

	AG/24/10 
	Develop a detailed implementation plan for the translation of the Teagasc 2023 MACC and incorporation where appropriate into the Climate Action Plan 
	New/updated measures from the Teagasc MACC included in the Climate Action Plan 
	Q3 2024 
	Complete 
	Action Complete 

	AG/24/16 
	Develop a system for the monitoring and reporting of methane reducing feed and manure ingredients 
	Develop a system for the monitoring and reporting of methane reducing feed and manure ingredients 
	Q4 2024 
	Delayed 
	Development of a monitoring & reporting system is progressing 

	AG/24/18 
	Develop a pilot programme for the incorporation of methane reducing additives (enteric and manure) within the Signpost dairy farms 
	On-farm demonstration of the feasibility of the incorporation of methane reducing feed additives, and generation of farm specific carbon footprints 
	Q4 2024 
	Complete 
	Action Complete 

	AG/24/26 
	Development of ecosystem services through the creation of a carbon farming framework 
	Draft framework published 
	Q2 2024 
	Delayed 
	Discussions on the development of policy for Carbon farming are progressing 

	AG/24/8 
	Deliver a range of knowledge transfer activities promoting the importance and benefits to farmers of optimising nutrient management strategies as a key contributor to reduced gaseous emissions 
	Farmer engagement in Signpost Advisory Programme Engage and support 20,000 farmers in the Signpost Advisory Programme, 4,500 farmers in Derogation Scheme support and 15,000 farmers in ACRES. Analyse and provide feedback on at least 50,000 soil samples. 
	Q4 2024 
	Delayed 
	Teagasc continues to deliver a range of knowledge transfer activities, and this action is progressing 

	JM/24/3 
	Support piloting, demonstration and innovation for a sustainable and circular bioeconomy 
	Grant agreements in place with approved projects to advance initiatives for a competitive bioeconomy 
	Q4 2024 
	Delayed 
	The grant agreements for approved projects are progressing 

	JM/24/5 
	Support research, knowledge transfer and monitoring activities on rewetting measures for farmed peat soils through the Midlands Carbon Catchment Study 
	Consortium appointed to deliver on the objectives of the Midlands Carbon Catchment Study (MCCS) 
	Q4 2024 
	Delayed 
	This action is progressing 

	LU/24/4 
	Review the proposed measures detailed in the Teagasc MACC to determine which actions are possible to deliver sustainably across all land use types 
	Report completed & under consideration 
	Q3 2024 
	Complete 
	Action Complete 

	AG/23/23 
	Consider the recommendations arising from the NESC report on Just Transition in Agriculture and develop suitable responding actions for inclusion in CAP 24. 
	Implementation Report with a focus on engagement, resources and policy. 
	Q3 2023 Delayed 
	Complete 
	Action Complete 



