## Current Projects
School_Name | Roll_Number | Current Stage | Stage 1 Start Date | Stage2a Start Date | Stage2b Start Date | Stage3 Start Date | Stage4 Start Date | Start On Site Date | Total_Project_Brief
Ceann Eitigh NS | 16802C | Stage 1 | 2024-05-29 | [5 empty] | 1 Mainstream classroom, Reconfiguration of 1 SET room to provide 2 SET rooms
Clonaghadoo NS | 16160L | Stage 2a | 2019-10-08 | 2021-03-11 |  |  |  |  | 1 SEN classroom with Central Activities Space and Daily Living Skills room
Cloneyhurke NS | 15923J | Stage 1 | 2018-07-04 | [5 empty] | 1 SET room and ancillary
Geashill 1 NS | 09191I | Stage 2b | 2022-09-14 |  | 2025-05-28 |  |  |  | 1 SEN classroom with Central Activities Space
Scoil Colmain Naofa | 17746A | Stage 2b | 2022-06-15 |  | 2025-05-02 |  |  |  | 2 SET rooms (prefab replacement) , 1 SET (New Build)
SN Chartaigh Naofa | 20273A | Stage 2b | 2018-05-17 | 2023-04-18 | 2024-05-08 |  |  |  | 3 Early intervention classrooms and reconfiguration works to existing classrooms
SN Mhuire Bainrioghan | 17336E | Stage 2b | 2020-04-09 | 2023-05-11 | 2023-08-14 |  |  |  | 1 SEN classroom
SN Osmann | 07949I | Stage 2b | 2024-02-21 |  | 2025-07-02 |  |  |  | 1 Mainstream classroom, 2 SET and ancillary
SN Phroinsiais Naofa | 18406E | Stage 4 | 2020-05-29 | 2021-11-29 | 2022-04-11 | 2023-04-13 | 2026-02-17 | TBC | 2 Mainstream classrooms (prefab replacement) 1 Mainstream classroom, 3 SET rooms, 1 SEN classroom
SN Seosamh | 07191V | Stage 2b | 2021-05-25 | 2022-07-15 | 2022-09-05 |  |  |  | 1 SEN classroom with Central Activities space and 1 SET (prefab replacement)
SN Seosamh | 17003A | Stage 4 | 2020-02-04 | 2021-11-15 | 2021-11-15 | 2022-05-12 | 2022-05-18 | 2022-05-18 | 1 Mainstream classroom, EWS - External works, SWS 2021 - Roof repairs and external works
St. Brendan's Monastery | 12370C | Stage 4 | 2020-06-18 | 2022-01-13 | 2022-09-14 | 2023-06-19 | 2025-02-07 | 2025-05-19 | 3 SEN classrooms, Reconfiguration works to provide 2 SET rooms
Coláiste Choilm | 65610S | Stage 4 | 2020-04-15 | 2022-04-11 | 2022-11-28 | 2024-08-15 | 2025-05-29 | 2025-05-29 | 3 Mainstream classroom, 1 Technology room and prep area, 2 Science lab and prep area, 1 DCG room, 1 Art room, 1 Multimedia room, 2 SEN
Coláiste Naomh Cormac | 72520I | Stage 1 | 2020-06-18: 2024-05-22 | 1 Art room and store 2 SEN classrooms, Refurbishment of of Science labs
Edenderry Convent NS | 16013V | Stage 1 | 2020-06-18: 2021-01-19 | 2 SEN, Toilet and fire upgrade: SWS (oil to gas project)
Killina Presentation Secondary School | 65630B | Stage 1 | 2020-06-18: 2022-03-09 | 3 Mainstream classroom, 1 Graphics room, 1 Technology room and prep area, 1 project store. 1 SET, Masterplan only for PE hall
Shinchill NS | 17031F | Stage 4 | 2018-09-29 | 2022-10-11 | 2022-11-10 | 2024-08-15 | 2026-03-26 | 2026-03-26 | 2 SEN classrooms, 1 Mainstream classroom (prefab replacement)
SN Mhuire | 18115Q | Stage 3 | 2020-11-20 | 2022-01-24 | 2023-02-08 | 2024-10-29 |  |  | 2 SEN, 1 Mainstream classroom (prefab replacement ), 1 Staffroom, Repurposing of existing staffroom to 1 SET room & repurposing works for SEN classroom
St. Brendan's Community School | 91491L | Stage 2b | 2020-06-18: 2019-12-09; 2022-01-13: 2022-02-17; 2022-09-14: 2024-04-23 | 3 SEN classrooms, Summer works windows replacement project.
St. Mary's Secondary School | 65582Q | Stage 2a | 2020-06-18: 2020-10-19; 2022-01-13: 2025-05-16 | 4 Mainstream classroom (prefab replacement), 1 Construction room (prefab replacement), 4 SEN (prefab replacement)
Tullamore College | 72560U | Stage 1 | 2020-06-18: 2024-05-22 | 11 Mainstream classroom, 3 Science lab, 1 Multimedia room, 2 SET rooms, 2 SEN