| CAP Year | Action Number | Action | Steps Necessary for Delivery | Output | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 2024 | IC/24/1 | Increase Ireland’s year-on-year climate finance contribution for 2024 | Scale up international climate finance through existing channels of support, introducing new funding initiatives and enhancing reporting on the gender- responsiveness of Ireland’s international climate finance as part of the Ireland’s overall climate finance reporting | Submission of official 2023 climate finance figures to EU, which show progress in scaling up Ireland’s climate finance | Q4, 2024 (EU reporting) Annual climate finance report delivered Q1, 2025. | Complete. 2023 Climate Finance figures submitted to EU in Q3. Annual Climate Finance Report (2023) published in Q1, 2025, following full verification of figures. Ireland provided €159.2 million in international climate finance in 2023, an increase of 32% from 2022. Over 80% of Ireland's bilateral climate finance in 2024 included a focus on gender equality. DFAT has since published final climate finance figures for 2024, which totalled €207.7 million, a 30% increase on 2023. |
| 2023 | IC/23/1 | Provide at least €225 million per year in Climate Finance to developing countries by 2025 | Scale up international climate finance through existing channels of support, introducing new funding initiatives and enhancing reporting on the gender- responsiveness of Ireland’s international climate finance as part of the Ireland’s overall climate finance reporting. | Delivery of annual Climate Finance reporting to the EU and Ireland’s annual Climate Finance report | Q4, 2023 (EU reporting) Annual climate finance report delivered Q1, 2024. | Complete. 2022 Climate Finance figures submitted to EU, Q3. Annual Climate Finance Report (2022) published in Q1, 2024, following full verification of figures. Ireland provided €120 million in international climate finance in 2022, an increase of 21% from 2021. Over 80% of Ireland's bilateral climate finance in 2023 included a focus on gender equality. |
|  | IC/23/1/A |  | Strategy for Small Island Developing States | Publication of Second National Strategy for Ireland’s engagement with Small Island Developing States | Q2 2023, delivered Q4 | Complete. Second National Strategy for Ireland’s engagement with Small Island Developing States approved by Cabinet in June 2023, launched December 2023. |
|  | IC/23/3 | Achieve constructive participation across multilateral environment fora | Constructive participation in negotiations on a new international legally binding instrument under the United Nations Convention on the Law of the Sea on the conservation and sustainable use of marine biological diversity of areas beyond national jurisdiction. | Conclusion of an ambitious legally binding instrument on marine conservation in the high seas | Q1 2023 | Complete. Negotiations concluded successfully at the United Nations on a draft agreement to ensure the conservation and sustainable use of marine biological diversity of areas beyond national jurisdiction in March 2023. Final agreement under the United Nations Convention on the Law of the Sea on the Conservation and Sustainable Use of Marine Biological Diversity of Areas beyond National Jurisdiction (BBNJ Agreement) adopted on 19 June 2023. Ireland played an active role in the BBNJ negotiations as part of the EU team, ratified the Agreement on 23 September 2025, and welcomed its entry into force on 17 January 2026. |
| 2021 | 445a | Make efforts through our diplomacy to ensure that climate change is recognised as a driver of instability and climate action is an opportunity for peacebuilding in multilateral fora where appropriate | Co-chair the Informal Experts Group on Climate and Security for 2021, and through this role and our contribution at the Security Council, strengthen the integration of climate considerations into discussions and resolutions on peace and security. |  | Q4 2022 | Complete. All relevant United Nations Security Council resolutions and mandate renewals reviewed to include, strengthen, or defend (depending on the context) language recognising links between climate change and instability. |
|  | 445b |  | Through our multilateral diplomacy at the EU, UN and other fora highlight the risks that climate change poses to international peace and stability and propose mitigating actions. Highlight also the opportunities for peacebuilding through climate action |  | Q4 2022 | Complete. Ireland worked within the EU, the Organisation for Security and Co-operation in Europe, the NATO Partnership group, at COP27 and in other fora, as relevant, to promote our position. |
|  | 446 | Place climate action, especially for Least Developed Countries and Small Island Developing States, at the heart of all development cooperation and policy partnerships, as well as our engagement in multilateral processes. | Ensure climate action, especially for Least Developed Countries and Small Island Developing States, is reflected in the new Climate Diplomacy Strategy. |  | Q2 2022 | Complete. Climate Diplomacy Strategy included as part of the Climate Finance Roadmap (see Action 448). The Roadmap reflects the central place of climate action, especially for Least Developed Countries and Small Island Developing States, at the heart of Ireland’s development cooperation and policy partnerships, as well as engagement in multilateral processes. |
|  | 446a |  | Ensure climate action, especially for Least Developed Countries and Small Island Developing States, is reflected in Ireland’s bilateral and multilateral funding channels. |  | Q4 2021 | Complete Climate Action for Least Developed Countries and Small Island Developing States is a clear focus for Ireland's international climate finance and diplomacy. For example, Ireland is a founding member of the Champions Group, Ireland announced €2.1 million in funding for ocean initiatives at COP26 and Ireland has supported the Climate Security Mechanism in 2021. |
|  | 446b |  | Support efforts in Least Developed Countries and Small Island Developing States (SIDS) to develop innovative solutions to climate change challenges, including technology and data innovations |  |  | Complete. Financial support was provided to projects providing innovative solutions in Least Developed Countries and SIDS. Financial support was also provided to projects including innovation challenge funds (e.g. Climate-KIC) and projects which enhance capacity, data and technologies, including projects that support the development of early warning systems (e.g. Systematic Observations Financing Facility). Monitoring and evaluation of these projects is ongoing. |
|  | 447 | Constructive participation in negotiations on a new UN Convention on the Law of the Sea Implementing Agreement | Constructive participation in negotiations on a new UN Convention on the Law of the Sea Implementing Agreement for the conservation and sustainable use of marine biological diversity in areas beyond national jurisdiction |  | Q4 2022 | Complete. UN Member States did not manage to adopt a text in 2022. Subsequently completed, see IC/23/3. |
|  | 448 | Double, at least, the percentage of ODA spending on climate finance by 2030, and report on our expenditure each year | Climate Finance Roadmap developed in collaboration with other Departments |  | Q1 2022, delivered Q2 | Completewww.irishaid.ie/news-publications/press/pressreleasearchive/2022/july/government-publishes-its-international-climate-finance-roadmap.html published July 2022. |
|  | 448a |  | Annual reports produced on international Climate Finance expenditure (including ODA) across Government Departments |  | Q4 2022, delivered Q1 2023. | Complete. Annual Climate Finance Report (2021) published in Q1 2023, following full verification of figures. Ireland provided €99.6 million in international climate finance in 2021, representing 10.2% of ODA. |
|  | 449 | Develop and implement approaches to climate-proof all ODA, and continue to include climate as a core theme in strategy development in the countries where Ireland has a significant development cooperation programme | Provide technical support to HQ Units and Missions to ensure climate action is included in their strategic and business planning |  | Q3 2022 | Complete Climate proofing tender for implementation support completed in September 2022. Climate Proofing process, with external support, delivered over the subsequent period. Training related to climate action in bilateral country programming provided. Development of an updated framework for climate proofing official development assistance (ODA) subsequently completed. |