## Corporate Risks
Risk ID | Risk Title | Mapping to Strategic Actions in SoS 2023/25 | Mapping to National Risk Assessment 2024 | Description | Change from previous CRR | Mitigants | Additional Mitigations | Likelihood | Impact | Rating | Lead Owner(s) | Categories | Created Date | Date of Last Review
CRR-R001 | Cyber Attacks | Goal 3, Action 4 | Technological risks - cybersecurity | A cyber-attack incident occurring as a result of malicious actors that exploits the Department's IT systems, networks, platforms or devices leading to a disruption of Departmental operations. Also potentially leading to a loss of data giving rise to claims for damages and reputational damage | Risk re-worded. Mitigants brought to strategic level. | • Sufficient resources dedicated to cyber security • Appropriate cyber security infrastructure in place • Cyber security plan in place |  | 4 | 5 | 20 | A-M. Sherkle | Operational, Financial | 2023-02-26 | 2026-03-03
CRR-R002 | Data Security | Most closely related to Goal 3, Action 4 | Technological risks - data flows, storage and security | Disclosure, loss, change or destruction of the confidential and/or sensitive and/or secret information assets under our stewardship including personal data as defined under GDPR and Data Protection Act due to improper or inadvertent actions, leading to significant reputational damage and potential financial loss. | Risk re-worded. Mitigants brought to strategic level. | • IT, data protection and information security policies and procedures in place • Mandatory GDPR training in place • All devices are encrypted |  | 3 | 4 | 12 | A-M. Sherkle G. O'Leary | Operational, Strategic | 2023-09-07 | 2026-03-03
CRR-R003 | Legacy bespoke software | Most closely related to Goal 3, Action 4 | Technological risks - data flows, storage and security | Inability to ensure continued operation of business critical bespoke ICT applications that run on legacy platforms due to a limited availability of appropriately skilled resources to maintain and develop these applications leading to increased probability of system downtime/failure. | Risk re-worded. Mitigants brought to strategic level. | • A modernisation programme of work has commenced on the platform |  | 2 | 4 | 8 | AM. Sherkle M. Clohessy | Operational | 2023-12-06 | 2026-03-03
CRR-R004 | Insufficient funding to achieve DE objectives or to cover the costs arising | All goals and actions | Mix of several economic risks | Insufficient money allocated to the Department or Sector as result of Government decisions on available Exchequer funding leading to an inability to deliver the strategic objectives of the Department or resulting in the Department's committed and actual spend for a given year being greater than the Voted allocations available at year-end. | Risk re-worded. Mitigants brought to strategic level. | • Continue to pursue efficiency and effectiveness in the allocation of resources and the operation of the system • Carry out or commission analysis to examine efficiency and effectiveness in the allocation of resources • Use analysis and data to develop robust business areas to support proposals for ongoing investment in the education sector |  | 4 | 4 | 16 | D.Tatton | Financial, Strategic | 2023-08-30 | 2026-03-03
CRR-R005 | Return to remote working | Goals 1, 2 and 3 multiple actions | Environmental risks - Pandemics | A return to remote working due a public health, environmental, terrorism, extreme weather or similar threat leading to a reduction in the ability to work on an in-person basis within the Department | Risk re-worded. Mitigants brought to strategic level. Risk impact downgraded. | • Ongoing engagement with colleagues in in other departments on risks and responses • Technology solutions rolled out to support remote working • Business Continuity plans in place |  | 2 | 4 | 8 | G. O'Leary T Ó Ruairc | Operational, Financial | 2023-02-26 | 2026-03-03
CRR-R005 | Return to remote learning | Goals 1, 2 and 3 multiple actions | Environmental risks - Pandemics | A return to remote learning for an extended period of time due a public health, environmental, terrorism, extreme weather or similar threat leading to a reduction in the ability for students to attend school on an in-person basis | Risk re-worded. Mitigants brought to strategic level. Risk impact downgraded. | • Guidance developed for schools on COVID-19 • Working Group in place to determine future remote learning policy |  | 2 | 5 | 10 | C.O'Neill, A. Conduit | Operational, Financial | 2023-02-26 | 2026-03-03
CRR-R006 | Ensuring sufficient school places | Goal 3, action 1 | Capacity constraints and infrastructure deficit | Not having sufficient school places to accommodate significantly increased numbers of pupils in the education system, due to the migration trends outside of planned scenarios leading to pressure on school places and physical infrastructure | New risk added | • Regular monitoring of key demographic and school enrolment data for every area of the country • Introduction of town by town level analysis where hot spots identified • Close engagement with stakeholders to ensure timely provision of accurate data on actual local school place needs and available capacity • Support co-ordination and efficiency in allocating school places to children from migrant background and insuring their integration into our schools via the REALT structures • Ongoing engagement with colleagues in D/Children, D/Housing, D/Taoiseach, D/Justice, Home Affairs and Migration on responses. • Scenario planning exercises conducted on a regular basis in PBU. |  | 4 | 4 | 16 | H. Loftus | Operational, Strategic | 2024-04-26 | 2026-03-03
CRR-R007 | Department's Capability | Goal 4, action 3 | Capacity constraints and infrastructure deficit | Inadequate numbers of staff and/or without the necessary skills within the Department to deliver on commitments for the education system due to limited workforce planning leading to sub-optimal policy and operational development and implementation. | New risk added | • A workforce planning division has been established with increased focus on strategic HR activities • An action group has been established looking at how the Department is organised, how staff are supported and how staff have access to the appropriate environment, resources and systems to enable the highest performance for the Department |  | 4 | 4 | 16 | T Ó Ruairc | Operational, Reputational, Financial | 2024-04-22 | 2026-03-03
CRR-R008 | Sectoral Capability | Goal 1, action 2 | Capacity constraints and infrastructure deficit | Inadequate numbers of staff and/or without the necessary skills being in place within the teaching and associated professions, particularly in large urban areas, to deliver on commitments for the education system due to limited workforce planning leading to sub-optimal policy and operational development and implementation. | New risk added | • A workforce planning division has been established to develop a workforce plan for the sector. • A project to develop recommendations for a strategic workforce plan for teachers supported by the EU (DG REFORM) is being undertaken by UNESCO. |  | 4 | 4 | 16 | T Ó Ruairc | Operational, Financial | 2024-04-22 | 2026-03-03
CRR-R009 | Financial Governance & Compliance | Goal 4, action 1 | None - operational risk | Failure to safeguard public funds as a result of inadequate financial governance and control leading to possible error or impropriety in Vote management and/or irregularity of transactions across the Vote. | Mitigants brought to strategic level. | • Comprehensive set of Financial Policies and Procedures in place in line with Government Spending Codes, relevant Circulars and legal obligations, including an Approvals procedure, a Fraud Policy, Procurement Policy and Protected Disclosures Policy. • An effective financial control environment with appropriate processes and procedures in place to record, profile, monitor, control and report on expenditure and budgets. • Ongoing systematic monitoring by budget holders of expenditure, controls and compliance / governance. • Governance and compliance systems including SLAs, MOUs or other formal structures in place with agencies, agents or other bodies. • A rigorous programme of work by a properly resourced Internal Audit Unit with an independently chaired Audit Committee. |  | 3 | 4 | 12 | B. McNally, T Ó Ruairc | Financial | 2023-02-26 | 2026-03-03
CRR-R010 | Significant interruption to services | Several actions in goals 3 and 4 | Mix of several risks | Inability to ensure business continuity due to floods, power failure etc leading to a reduction in effectiveness of the Department | Risk re-worded. Mitigants brought to strategic level. | • Business Continuity Plans in place for Department business units • Disaster recovery plans in place for ICT systems |  | 3 | 4 | 12 | D.Tatton, AM. Sherkle | Operational, Financial | 19/5/2023 | 2026-03-03
CRR-R011 | Long term strategic planning | Goal 4, Action 4 | None - operational risk | Lack of capacity for senior leaders due to the number of competing demands for their time leading to a scarcity of time to progress the key strategic issues for education | Risk re-worded and based on MB response to key risks as outlined in IPA report. | • Four action groups have been established to lead out on strategic areas • A Strategy and Development unit has been established to lead on the vision for the future of education • Additional senior level posts have been approved to support key priority areas • The Organisational Capability Review has provided direction in this area |  | 4 | 4 | 16 | B. McNally | Strategic | 2023-02-26 | 2026-03-03
CRR-R012 | Governance of Agencies and Funded Bodies | Goal 3, Action 5 | None - operational risk | Failure to implement effective governance, compliance and performance management within the Department in line with legislation and relevant frameworks with respect to its role in oversight of bodies under aegis and funded bodies due to the absence or suboptimal working of robust structures, staffing or processes leading to significant reputational damage and potential financial risk. | Risk re-worded. Mitigants brought to strategic level. | • Relevant Divisions/Units have clearly delineated responsibilities set out for the oversight, governance and performance management of bodies under remit in accordance with statutory requirements and the Code of Practice for Governance of State Bodies • An SG chaired Management Board sub committee on sectoral governance and accountability is in place • Sectoral Governance Unit established a Framework Oversight Plan for State Bodies under the aegis of the department | Work has commenced on a framework to support standardising oversight for funded bodies | 3 | 4 | 12 | A.Conduit, M.Mannion, C. O'Neill G.O'Leary | Financial, operational | 2023-02-26 | 2026-03-03
CRR-R013 | Litigation | Goal 4, action 1 | None - operational risk | Failure to implement effective governance and compliance within the Department in line with legislation due to the absence or suboptimal working of robust structures, staffing or processes leading to the risk of litigation and significant reputational damage and potential financial risk. | New risk split out from previous risk | • Support provided by legal services to line divisions through provision of advices, managing cases on hand and oversight of legislative programme by CPU • Appropriate structures in place (e.g. MB, Risk Committee, Audit Committee, Internal Audit Unit, Business Planning, PMDS) • Adequate resourcing and oversight of these structures to ensure their effectiveness |  | 2 | 5 | 10 | G. O'Leary, D.Tatton | Operational, Strategic | 2023-02-26 | 2026-03-03
CRR-R014 | Child Protection | Goal 2, action 1 | None - operational risk | Significant breach of the Department's Child Protection Procedures for Schools and/or lack of follow up on concerns brought to the attention of Departmental staff due to poor processes leading to harm to a child. | Risk re-worded. Mitigants brought to strategic level. | • Child Protection Oversight Group in place with quarterly reports to Management Board • Safe Provision of Schooling visits and Child Protection and Safeguarding Inspections in place • Review of Child Protection Procedures for staff underway to ensure robust processes in place that are clearly communicated to staff |  | 2 | 5 | 10 | C.O'Neill, Y.Keating, A.Conduit | Operational | 2023-02-26 | 2026-03-03
CRR-R015 | Inclusion | Goal 2, multiple actions | None - operational risk | Children and young people experience a less inclusive education due to the absence, or sub-optimal working of, robust structures, staffing or processes either within the Department or within the sector leading to poorer educational outcomes for the child and risk of litigation and reputational damage for the Department. | New risk | • An action group has been established to examines how to ensure that children and young people experience the highest quality, and most inclusive, education possible • Sufficient resources and infrastructure are put in place to support inclusion in areas such as Special Educational Needs, social disadvantage and other groups at risk of educational disadvantage • Key strategies and policies in these areas are in place and are subject to evaluation |  | 2 | 5 | 10 | M.Mannion, Y.Keating, C.O'Neill, A. Conduit | Operational | 2024-05-14 | 2026-03-03
CRR-R016 | Quality | Goal 1, multiple actions | None - operational risk | Children and young people experience a lower quality educational experience due to the sub-optimal application of educational practice leading to poorer educational outcomes for the child and a risk of litigation and reputational damage for the Department. | New risk | • An action group has been established to examine how to ensure that children and young people experience the highest quality, and most inclusive, education possible • Sufficient resources and infrastructure are put in place to support quality through areas such as the Inspectorate • Key strategies and policies are in place and are subject to evaluation |  | 2 | 5 | 10 | C.O'Neill, M.Mannion Y.Keating, A.Conduit | Operational | 2024-05-14 | 2026-03-03
CRR-R017 | Leadership and Governance | Goal 3, multiple actions | None - operational risk | Inefficient and/or ineffective leadership or governance within the school sector due to the absence, or sub-optimal working of an effective leadership and governance framework leading to leading to reputational damage for the Department and potentially sub-optimal use of Exchequer funding. | New risk | • An action group has been established to examine how the Department can support the most effective and efficient leadership and governance of the school sector |  | 2 | 5 | 10 | D.Tatton, C.O'Neill, Y.Keating | Strategic, Operational | 2024-05-14 | 2026-03-03
CRR-R018 | Integration of Youth Affairs into the department | N/A | None - operational risk | Risk of integration of Youth Affairs unit into the department not meeting its full potential leading to sub-optimal outcomes for users of youth services |  | • Cross-Departmental Integration Plan developed and being executed • Additional senior staff from within the department appointed to Youth Affairs to support integration • Multiple communications vehicles to drive linkages with Youth Afffairs and existing policies/services |  | 2 (NR) | 3 (NR) | 6 (NR) | C.O'Neill | Strategic, Operational | 2025-07-14 | 2026-03-03 | Propose close this risk
CRR-R019 | Industrial Action | N/A | None - operational risk | Risk of reduced quality of education for students in schools due to sustained industrial action within school communities leading to poorer educational outcomes for students |  | Industrial relations Forums and Structures in place to support engagement with all education stakeholders |  | 3 | 4 | 12 | T Ó Ruairc C O’Neill D Tatton | Strategic, Operational | 2025-08-01 | 2026-03-03